## KPI Target
IP Creation | IP Translation | Visibility | Staff Improving
Key Activities
Plan, Feedback, Knowlenge Sharing

## Plan
Task ID | Definition | Milestone | Deadline
X1: Misc |  | POC demo of 2 Quantum Safe Gateway | 24th April
X2: Project Management
X3: My R&D
X4: P5C-Shijing
X5: P5C-Yiwen
X6: P5C-Yuanchen |  | 1. Gateway Web dashboard UI change. 2. Gateway Hub dashboard.(Show all the gateway status in one page) | 3. Gateway C version client integration
X7: P5C-RF1
X8: P5C-RF2
X9: Theme3-Junwen
X10: Theme 2-Ee-Chien
X11: Theme 4 QKD
X12: Interns
X13: RO

## MonthlyReport-2020
Overall Status |  | 2 | 172.5 | 0 |  | 1% |  |  | 32.5% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 7560% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
Expected Status | [5 empty] | 37.89% |  |  | 37.89% |  |  | 37.89% |  |  | 37.89% |  |  | 37.89% |  |  | 37.89% |  |  | 37.89% |  |  | 37.89% |  |  | 37.89% |  |  | 37.89% |  |  | 37.89% |  |  | 37.89% |  |  | 37.89%
Starting Date | [5 empty] | 2020-03-16 |  |  | 2020-03-16 |  |  | 2020-03-16 |  |  | 2020-03-16 |  |  | 2020-03-16 |  |  | 2020-03-16 |  |  | 2020-03-16 |  |  | 2020-03-16 |  |  | 2020-03-16 |  |  | 2020-03-16 |  |  | 2020-03-16 |  |  | 2020-03-16 |  |  | 2020-03-16
Deadline | [5 empty] | 2021-03-31 |  |  | 2021-03-31 |  |  | 2021-03-31 |  |  | 2021-03-31 |  |  | 2021-03-31 |  |  | 2021-03-31 |  |  | 2021-03-31 |  |  | 2021-03-31 |  |  | 2021-03-31 |  |  | 2021-03-31 |  |  | 2021-03-31 |  |  | 2021-03-31 |  |  | 2021-03-31
Actual Completion Date
Review by RO | Month (Date of 1st day, DD/MM/YYYY) | Report Time (DD/MM/YYYY) | Working Hours | Leaves (Day) | Oerall Remarks in a month | X1: Misc |  |  | X2: Project Management |  |  | X3: My R&D |  |  | X4: P5C-Shijing |  |  | X5: P5C-Yiwen |  |  | X6: P5C-Yuanchen |  |  | X7: P5C-RF1 |  |  | X8: P5C-RF2 |  |  | X9: Theme3-Junwen |  |  | X10: Theme 2-Ee-Chien |  |  | X11: Theme 4 QKD |  |  | X12: Interns |  |  | X13: RO
[6 empty] | Progress in a month (Percentage) | Working Hours | Remark | Progress in a month (Percentage) | Working Hours | Remark | Progress in a month (Percentage) | Working Hours | Remark | Progress in a month (Percentage) | Working Hours | Remark | Progress in a month (Percentage) | Working Hours | Remark | Progress in a month (Percentage) | Working Hours | Remark | Progress in a month (Percentage) | Working Hours | Remark | Progress in a month (Percentage) | Working Hours | Remark | Progress in a month (Percentage) | Working Hours | Remark | Progress in a month (Percentage) | Working Hours | Remark | Progress in a month (Percentage) | Working Hours | Remark | Progress in a month (Percentage) | Working Hours | Remark | Progress in a month (Percentage) | Working Hours | Remark
| 2020-03-16 | 2020-03-30 | 90.5 |  |  | 1% | 2 |  | 32.5% | 2.5 |  |  | 5 |  |  | 1 |  |  | 1 |  | 60% | 72 | 1. Gateway Web dashboard UI change: 1.1 half circle gauge data's unit was changed to Kbps. 1.2 Refresh key button disabled for 2 sec after user has pressed it. 1.3 Added the peak value (max) at the bottom of each chart panel. 2.Gateway Hub dashboard.(Show all the gateway status in one page): 2.1Added the deployed gateway information panel.(click the gateway name will link to each gateway's Individual page ) 2.2 Added all gateway history of exception log information display panel. 3.Gateway C version client integration : 3.1 finished the C version data report API. 4 Intern online interview. |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1
| 2020-05-01 | 2020-05-31 | 82 |  |  |  | 3 |  |  | 2 | [10 empty] | 75 | 77 | 1. Fixed the assignment document and the time plan for new intern Zhao Ming. 2.Finished the QSG-Topographic-Map web panel to show the communication state of different gateway devices. 3. Added an Android security key storage document for knowledge sharing.
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  |  | 0 | [19 empty] | 1. Fixed the assignment document and the time plan for new intern Zhao Ming.
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## summer intern interview result
Name | GPA | Interest area | Private project workload. | Task selected | Technical questions Solved | Select priority
Yan Wei Liang | 4.62; 2 SU core modules | Web design | Github 408 commits in the last year | 3. Gateway Deployment Map Panel. | Selected 1 Questions.Qestion3 both basic knowledge and problem solving answer are correct | 2
Jun Hao | 3.83; 1 SU core modules | Web design | Not provided | 2. Server IP Deployment Hub.3. Gateway Deployment Map Panel. | Selected 3 Questions.Question-1 basic knowledge answer is correct.Question-2 basic knowledge answer is correct. Problem solving answer very close to correct one.Question-3 both basic knowledge and problem solving answer are correct. | 2
Zhao Ming | 4.39; 2 SU core modules | Web design | Answered 150+ Kattis questions | 3. Gateway Deployment Map Panel. | Selected 3 Questions.Question-1 basic knowledge answer is correct.Question-2 basic knowledge answer is correct.Question-3 both basic knowledge and problem solving answer are correct | 1
Jie Wu | 4.52; 2 SU core modules | Web design and data analyzation | Not provide. | 1. Gateway Feedback Data Analyzation Program.3. Gateway Deployment Map Panel. |  | 3

## WeeklyReport-2020
Overall Status |  | 19 | 348 | 0 |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 1020% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
Expected Status | [5 empty] | 37.89% |  |  | 37.89% |  |  | 37.89% |  |  | 37.89% |  |  | 37.89% |  |  | 37.89% |  |  | 37.89% |  |  | 37.89% |  |  | 37.89% |  |  | 37.89% |  |  | 37.89% |  |  | 37.89% |  |  | 37.89%
Starting Date | [5 empty] | 2020-03-16 |  |  | 2020-03-16 |  |  | 2020-03-16 |  |  | 2020-03-16 |  |  | 2020-03-16 |  |  | 2020-03-16 |  |  | 2020-03-16 |  |  | 2020-03-16 |  |  | 2020-03-16 |  |  | 2020-03-16 |  |  | 2020-03-16 |  |  | 2020-03-16 |  |  | 2020-03-16
Deadline | [5 empty] | 2021-03-31 |  |  | 2021-03-31 |  |  | 2021-03-31 |  |  | 2021-03-31 |  |  | 2021-03-31 |  |  | 2021-03-31 |  |  | 2021-03-31 |  |  | 2021-03-31 |  |  | 2021-03-31 |  |  | 2021-03-31 |  |  | 2021-03-31 |  |  | 2021-03-31 |  |  | 2021-03-31
Actual Completion Date
Review by RO | Week (Date of 1st day, DD/MM/YYYY) | Report Time (DD/MM/YYYY) | Working Hours | Leaves (Day) | Oerall Remarks in a week | X1: Misc |  |  | X2: Project Management |  |  | X3: My R&D |  |  | X4: P5C-Shijing |  |  | X5: P5C-Yiwen |  |  | X6: P5C-Yuanchen |  |  | X7: P5C-RF1 |  |  | X8: P5C-RF2 |  |  | X9: Theme3-Junwen |  |  | X10: Theme 2-Ee-Chien |  |  | X11: Theme 4 QKD |  |  | X12: Interns |  |  | X13: RO
[6 empty] | Progress in a week (Percentage) | Working Hours | Remark | Progress in a week (Percentage) | Working Hours | Remark | Progress in a week (Percentage) | Working Hours | Remark | Progress in a week (Percentage) | Working Hours | Remark | Progress in a week (Percentage) | Working Hours | Remark | Progress in a week (Percentage) | Working Hours | Remark | Progress in a week (Percentage) | Working Hours | Remark | Progress in a week (Percentage) | Working Hours | Remark | Progress in a week (Percentage) | Working Hours | Remark | Progress in a week (Percentage) | Working Hours | Remark | Progress in a week (Percentage) | Working Hours | Remark | Progress in a week (Percentage) | Working Hours | Remark | Progress in a week (Percentage) | Working Hours | Remark
| 2020-03-16 | 2020-03-20 | 19 | [17 empty] | 40% | 12 | 1. Added the deployed gateway information panel.(click the gateway name will link to each gateway's Individual page ) 2. - Added all gateway history of exception log information display panel. |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1
| 2020-03-23 | 2020-03-30 | 11 | [17 empty] | 70% | 11 | 1. Didi four intern online interview
| 01/04/2020' | 10/04/2020' | 20 | [17 empty] | 50% | 20 | 1. Added knowleage sharing topic.2. Improve the communication protocal
| 13/04/2020' | 21/04/2020' | 25 | [17 empty] | 55% | 25 | 1. Add one knowledge sharing topic about UDP.2. Fixed the UDP communication part diconnection error.3. Continous to do DPDK set up.
| 2020-04-23 | 2020-04-26 | 18 | [17 empty] | 45% | 18 | 1. Added function to handle the sending data (like a video/file) bigger than UDP buffer for the communication module[udpCom.py](This module is used to upload the gateway data to the database server).
| 2020-04-27 | 2020-04-30 | 22 | [17 empty] | 60% | 22 | 1. Added the report data Queue so and split the data process part in a separate thread, So the server can response the client faster when a big number of client has connected to the server.
| 2020-05-04 | 2020-05-09 | 13 | [17 empty] | 60% | 13 | Added a knowledge share document about the UDP channel closed problem.
| 2020-05-11 | 2020-05-17 | 19 | [17 empty] | 55% | 19 | 1. Fixed the assignment document and the time plan for new intern Zhao Ming. 2.Added an Android security key storage document for knowledge sharing.
| 2020-05-18 | 2020-05-22 | 25 | [17 empty] | 70%L16:V16K16:V16J16:V16X14M16:V16I16:V16H1F16:V16 | 25 | Finished the QSG-Topographic-Map web panel to show the communication state of different gateway devices
| 2020-05-25 | 2020-05-29 | 20 | 0 | [16 empty] | 50% | 20 | Made the map data update simulator program. The Node's activation states and the link with the link states will be generate in the DataMgr module. The inactivate link we will change its color to gray.
| 2020-06-01 | 2020-06-08 | 21 | [17 empty] | 65% | 21 | Do code review with intern ZhaoMing. Added the function to show all the node information on the makers' pop-up information box. Updated the project design document, Problem and Solution document and the readme file.
| 2020-06-09 | 2020-06-14 | 20 | [17 empty] | 70% | 20 | 1. Update the design document of the QSG-Topographic-Map project. 2 Fixed the web-page control and filter check box program. 3 Added the parameter handler in the QSG-Topographic-Map to so it can show the 2 gateways communication states in the individual gateway information display page.
| 2020-06-15 | 2020-06-20 | 19 | [17 empty] | 45% | 19 | 1. Improved the Gateway client IP/Information configure distribution manager server program. Function added: The server will feedback the Init ID confirm information, update rate, GPS registered feedback and the data base updated feed back to the client. So when a used client is moved to another place, when it is connected again, all the data in the control hub will update automatically. 2. Added the multi-request handling function in the map server to handle multiply map update request. 3. Improved the project design document to add 2 more function for intern ZhaoMing to work on.
| 2020-06-22 | 2020-06-27 | 14 | [17 empty] | 40% | 14 | 1. Added the gateway throughput diagram marker to indicate the time of key refresh. 2. Added the gateway information report rate adjustment dropdown menu and started to re-make the gateway information display panel. (Added the template web and CSS file, so the map, information area, communication link display panel will use this template and follow the same design style.)
| 2020-06-29 | 2020-07-03 | 21 | [17 empty] | 50% | 21 | 1. Built the “Log.py” module which used to log all the server program running state for debug trace back.(It contents auto log Info/warning/error/detail, auto rollover when the log file more than 10Mb) We will use this module replace all the system build in print() function in python. 2. Added the database fetch model for ZhaoMing’s QSG_Topographic_Map program to link ZhaoMing’s program with our current gateway update information database.
| 2020-07-06 | 2020-07-11 | 20 | [17 empty] | 55% | 20 | 1. Test setup docker image on Ubuntu. 2. Try to built the qsvpn project generated by YiWen.(still working) 3. Help ZhaoMing to do fix the development problem for database program integration.
| 2020-07-12 | 2020-07-17 | 21 | [17 empty] | 65% | 21 | 1. Improved the Log module added the roll over function to auto package the log file and save in specified folder. Added the function to clear the log which is older than a specific period. 2. Create the document about docker setup and usage in the container. 3. Do code review with ZhaoMing about the QSG-Topographic-Map and fixed some small bugs.
| 2020-07-20 | 2020-07-24 | 20 | [17 empty] | 70% | 20 | 1. Created the BgInit.py module to provide the control function for the program which running in the system background. So we can remotely control the server program from internet to change program parameters, start/restart, pause and stop the program. 2. Finished replacing all the python built in print/warning and except with Log.Info(), Log.warning(), Log.error() and Log.except() for QSG-Topographic-Map and QSG-Manger-Hub projects. 3. Created the project KPI document draft for the web design part and the code quality improvement part for the FY20/214. 4. Working on the intern Summery for ZhaoMing as his intern ship will end thin month.
| 2020-07-27 | 2020-07-30 | 0 | [17 empty] | 75% | 22 | 1.Added the legend in the QSG-Topographic-Map to show the different samples meaning and plugged the map in the gateway general dashboard. 2.Did final coder review with intern ZhaoMing for his internship project and created Zhaoming’s internship feedback report. 3.Integrating QSG-Topographic-Map backend part in to QSG-Manager’s dataMgr program.
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0